## 4.IAMandSecurityServices
Asset ID | Risk ID | Asset Name | Impact on Confidentiality | Impact on Integrity | Impact on Availability | Asset Value | Threats | Vulnerabilities | Risks | Existing Controls | Control Effectiveness | Probability | Impact | Risk Value | Priority for Risk Treatment | Risk Treatment Category | Actions or Additional Controls | Revised Probability | Revised Impact | Revised Risk Value
A0127 | R0127 | IAM (AWS, Azure, GCP) | 3 | 3 | 3 | 27 | 1. Unauthorized access 2. Privilege escalation 3. Account compromise 4. Insider threats | 1. Weak password policies 2. Misconfigured IAM roles 3. Lack of multi-factor authentication 4. Overly permissive policies | 1. Data breaches 2. Unauthorized system modifications 3. Denial of service due to account compromise | 1. Strong password policies 2. Enable multi-factor authentication 3. Implement least privilege access 4. Conduct periodic IAM role reviews 5. Log and monitor IAM activities | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Enforce strong password and MFA policies 2. Automate IAM role analysis tools 3. Conduct regular security training for IAM users | 1 | 4 | 108
A0128 | R0128 | AWS Cognito | 3 | 3 | 3 | 27 | 1. Unauthorized access 2. Credential theft 3. Account takeover 4. Insufficient session management | 1. Weak token validation 2. Misconfigured identity pools 3. Insecure application integration 4. Missing MFA enforcement | 1. Data breaches 2. Compromised user accounts 3. Unauthorized access to application data | 1. Enforce strong token validation policies 2. Require MFA for sensitive user groups 3. Secure application integration via best practices 4. Monitor user login behaviors 5. Conduct regular security assessments | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Automate user behavior monitoring 2. Implement anomaly detection for account activity 3. Regularly review IAM policies | 1 | 4 | 108
A0128 | R0128 | Azure Active Directory | 3 | 3 | 3 | 27 | 1. Credential compromise 2. Privilege escalation 3. Unauthorized access 4. Insider threats | 1. Misconfigured conditional access policies 2. Lack of multi-factor authentication (MFA) 3. Excessive admin privileges 4. Weak password policies | 1. Data breaches due to account compromise 2. Loss of system integrity 3. Service outages due to unauthorized admin actions | 1. Conditional access enforcement 2. MFA requirement 3. Privileged Identity Management (PIM) 4. Comprehensive logging and monitoring | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Regularly review and refine conditional access policies 2. Enforce stricter MFA requirements 3. Perform role-based access reviews | 1 | 4 | 108
A0129 | R0129 | AWS Shield | 3 | 3 | 3 | 27 | 1. DDoS attacks 2. Network-layer attacks 3. Application-layer attacks | 1. Insufficient monitoring of attack vectors 2. Misconfigured DDoS mitigation settings 3. Lack of integration with WAF | 1. Service unavailability due to DDoS 2. Compromised service performance 3. Revenue loss from downtime | 1. Automatic DDoS protection 2. Integration with AWS WAF 3. Real-time monitoring of traffic patterns 4. Preconfigured mitigation rules | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Conduct regular reviews of DDoS mitigation rules 2. Enable enhanced monitoring for critical resources 3. Automate alert responses | 1 | 4 | 108
A0130 | R0130 | GuardDuty | 3 | 3 | 3 | 27 | 1. Unauthorized access attempts 2. Malicious activity detection 3. Insider threats | 1. Limited coverage of custom threat intelligence 2. Insufficient configuration monitoring 3. Lack of real-time alert tuning | 1. Undetected threats leading to data breaches 2. Delayed incident response 3. Potential insider abuse | 1. Threat detection using machine learning 2. Integration with AWS CloudWatch for monitoring 3. Regular review of GuardDuty findings | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Enhance threat intelligence integrations 2. Regularly review and tune alerts 3. Automate response workflows | 1 | 4 | 108
A0131 | R0131 | Macie | 3 | 2 | 2 | 21 | 1. Unauthorized access to sensitive data 2. Insider threats 3. Exposure of sensitive data to the public | 1. Misconfigured data classification policies 2. Lack of real-time monitoring 3. Overly permissive access to data stores | 1. Data breaches leading to loss of sensitive information 2. Compliance violations 3. Insider misuse of data | 1. Automated sensitive data discovery 2. Integration with IAM policies 3. Centralized monitoring and logging of data access events | Effective | 2 | 4 | 84 | Priority-1 | Risk reduction | 1. Regularly review and refine classification rules 2. Enable alerting for unusual data access patterns 3. Strengthen IAM roles | 1 | 3 | 63
A0132 | R0132 | Security Command Center (GCP) | 3 | 3 | 3 | 27 | 1. Detection gaps in emerging threats 2. Misconfigured security policies 3. Insider threats | 1. Limited integration with external threat intelligence 2. Insufficient tuning of alerts 3. Gaps in vulnerability management | 1. Undetected threats leading to data breaches 2. Delayed incident response 3. Compliance violations | 1. Centralized visibility of assets 2. Automated threat detection 3. Integration with GCP IAM and Security Policies 4. Real-time alerts | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Enhance integration with threat intelligence feeds 2. Regularly review and refine security policies 3. Automate incident response workflows | 1 | 4 | 108
A0133 | R0133 | Azure Security Center | 3 | 3 | 3 | 27 | 1. Detection gaps in threats 2. Misconfigured security recommendations 3. Insider threats | 1. Limited automation in applying recommendations 2. Insufficient alert tuning 3. Lack of real-time integrations | 1. Data breaches from undetected threats 2. Delayed incident response 3. Compliance violations | 1. Centralized threat management 2. Integration with Azure Defender and Sentinel 3. Automated vulnerability assessments 4. Customizable alerting | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Automate enforcement of security recommendations 2. Regularly review and refine alerts 3. Improve response automation workflows | 1 | 4 | 108
A0134 | R0134 | KMS (AWS, GCP) | 3 | 3 | 3 | 27 | 1. Unauthorized access to encryption keys 2. Key compromise 3. Improper key lifecycle management 4. Insider threats | 1. Weak access controls 2. Lack of key rotation policies 3. Misconfigured IAM policies 4. Insufficient logging and monitoring | 1. Data breaches from compromised keys 2. Unauthorized decryption of sensitive data 3. Compliance violations | 1. Centralized key management 2. Enforced IAM access controls 3. Automated key rotation policies 4. Comprehensive logging of key usage | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Implement stricter access controls for keys 2. Regularly review key usage logs 3. Enhance key rotation and lifecycle policies | 1 | 4 | 108
A0135 | R0135 | Azure Key Vault | 3 | 3 | 3 | 27 | 1. Unauthorized access to secrets and keys 2. Key compromise 3. Insider threats 4. Misconfigured access policies | 1. Weak access policies 2. Lack of auditing and monitoring 3. Insufficient key rotation policies 4. Overly permissive roles | 1. Data breaches from exposed keys or secrets 2. Unauthorized decryption of sensitive data 3. Compliance violations | 1. Role-based access control (RBAC) 2. Comprehensive logging and monitoring 3. Key rotation and expiration policies 4. Integration with Azure AD | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Strengthen access control policies 2. Automate key rotation 3. Enhance monitoring and alerts for unauthorized access | 1 | 4 | 108
A0136 | R0136 | Secrets Manager (AWS, GCP) | 3 | 3 | 3 | 27 | 1. Unauthorized access to secrets 2. Insider threats 3. Exposure of sensitive secrets 4. Compromised APIs | 1. Weak access policies 2. Lack of secrets rotation policies 3. Insufficient auditing and monitoring 4. Overly permissive roles | 1. Data breaches from exposed secrets 2. Unauthorized service access due to leaked credentials 3. Compliance violations | 1. Centralized secrets management 2. Enforced IAM-based access control 3. Regular secrets rotation policies 4. Comprehensive logging and monitoring | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Strengthen IAM policies 2. Automate secrets rotation 3. Regularly review access logs and policies for secrets | 1 | 4 | 108
A0137 | R0137 | Config (AWS) | 3 | 3 | 3 | 27 | 1. Misconfigured resources 2. Unauthorized configuration changes 3. Insider threats | 1. Lack of real-time monitoring 2. Inadequate IAM policies for configuration changes 3. Insufficient logging | 1. Data breaches due to misconfigurations 2. Compliance violations 3. Disruption of services caused by unauthorized changes | 1. Continuous monitoring of resource configurations 2. Enforcement of IAM policies 3. Comprehensive logging of configuration changes | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Regularly review configuration change logs 2. Automate alerts for misconfigurations 3. Strengthen IAM policies for Config | 1 | 4 | 108
A0138 | R0138 | AWS WAF | 3 | 3 | 3 | 27 | 1. Malicious payload injection 2. DDoS attacks 3. Unauthorized access to web applications | 1. Weak or misconfigured WAF rules 2. Lack of real-time updates to threat intelligence 3. Insufficient logging and monitoring | 1. Data breaches through exploited vulnerabilities 2. Service disruption from DDoS attacks 3. Unauthorized web access | 1. Predefined managed WAF rules 2. Integration with AWS Shield for DDoS protection 3. Real-time traffic monitoring 4. Regular WAF rule reviews | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Regularly update WAF rules with the latest threat intelligence 2. Enhance monitoring and alerting for anomalous traffic | 1 | 4 | 108
A0139 | R0139 | CloudTrail | 3 | 3 | 3 | 27 | 1. Unauthorized access to logs 2. Insider threats 3. Tampering with audit trails | 1. Insufficient encryption for log files 2. Overly permissive access to CloudTrail logs 3. Lack of multi-region logging | 1. Loss of audit trail integrity 2. Delayed detection of malicious activities 3. Compliance violations | 1. Centralized logging across all regions 2. Encryption of logs using KMS 3. Strict IAM policies for accessing logs 4. Comprehensive monitoring of log activity | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Implement multi-region log replication 2. Strengthen access controls for log files 3. Automate alerts for unauthorized log access | 1 | 4 | 108
A0140 | R0140 | Cloud Audit Logs (GCP) | 3 | 3 | 3 | 27 | 1. Unauthorized access to logs 2. Insider threats 3. Log tampering | 1. Insufficient encryption for logs 2. Overly permissive access policies 3. Inadequate monitoring of log access | 1. Loss of audit trail integrity 2. Delayed detection of security incidents 3. Compliance violations | 1. Logging across all GCP projects 2. Encryption of logs using CMEK 3. IAM-based access controls for logs 4. Real-time log monitoring and alerting | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Enhance access controls for audit logs 2. Enable alerting for suspicious access 3. Conduct periodic log integrity checks | 1 | 4 | 108
A0141 | R0141 | AWS Policy | 3 | 3 | 3 | 27 | 1. Overly permissive policies 2. Policy misconfiguration 3. Unauthorized policy modifications | 1. Lack of role-based access control 2. Insufficient review of policy changes 3. Misconfigured IAM trust relationships | 1. Unauthorized access to sensitive resources 2. Compromised resource security 3. Compliance violations | 1. Use of least privilege principle 2. Regular review and audit of policies 3. IAM roles with strict access permissions 4. Policy change monitoring | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Implement automated policy review tools 2. Enhance monitoring of policy changes 3. Conduct periodic role and policy audits | 1 | 4 | 108
A0142 | R0142 | Azure Policy | 3 | 3 | 3 | 27 | 1. Policy misconfiguration 2. Overly permissive policies 3. Unauthorized modifications to policies | 1. Lack of automated enforcement 2. Insufficient policy monitoring 3. Ineffective policy scoping | 1. Unauthorized access to resources 2. Non-compliance with organizational standards 3. Security configuration drift | 1. Centralized policy management 2. Role-based access control (RBAC) for policy changes 3. Monitoring and alerting for non-compliance 4. Periodic policy audits | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Automate enforcement of policies using Azure Policy compliance features 2. Enhance real-time monitoring of policy violations | 1 | 4 | 108
A0143 | R0143 | Azure Blueprints | 3 | 3 | 3 | 27 | 1. Misconfigured blueprints 2. Unauthorized modifications to blueprint definitions 3. Insider threats | 1. Lack of role-based access control (RBAC) for blueprints 2. Insufficient auditing of blueprint changes 3. Weak compliance enforcement | 1. Non-compliance with organizational standards 2. Unintended exposure of sensitive resources 3. Configuration drift | 1. Centralized blueprint management 2. RBAC for managing blueprint definitions 3. Audit logging for blueprint assignments 4. Automated deployment compliance checks | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Automate auditing and enforcement of blueprint assignments 2. Enhance monitoring for unauthorized changes 3. Conduct periodic compliance reviews | 1 | 4 | 108
A0144 | R0144 | Azure Information Protection | 3 | 3 | 3 | 27 | 1. Unauthorized access to classified information 2. Data leakage 3. Insider threats | 1. Misconfigured classification labels 2. Inadequate enforcement of protection policies 3. Insufficient monitoring | 1. Exposure of sensitive data 2. Loss of data integrity 3. Compliance violations | 1. Automated classification and labeling of data 2. Integration with Azure AD for access control 3. Monitoring and logging of data access and usage | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Regularly review and refine classification labels 2. Automate enforcement of data protection policies 3. Enhance monitoring and alerting | 1 | 4 | 108
A0145 | R0145 | Azure Sentinel | 3 | 3 | 3 | 27 | 1. Detection gaps in advanced threats 2. Insider threats 3. Misconfigured analytics rules | 1. Lack of tuning for analytics rules 2. Insufficient integration with third-party data sources 3. Delayed alert response | 1. Undetected threats leading to data breaches 2. Delayed incident response 3. Compliance violations | 1. Integration with Azure Security Center 2. Customizable analytics and alerts 3. Centralized logging and threat hunting capabilities | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Regularly tune analytics rules and playbooks 2. Enhance integration with external threat intelligence feeds 3. Automate incident response workflows | 1 | 4 | 108
A0146 | R0146 | AWS Certificate Manager | 3 | 3 | 3 | 27 | 1. Expired or compromised certificates 2. Unauthorized access to certificates 3. Weak encryption algorithms | 1. Lack of automated certificate renewal 2. Insufficient monitoring of certificate expiration 3. Misconfigured access policies | 1. Data breaches due to compromised certificates 2. Service disruptions caused by expired certificates 3. Compliance violations | 1. Automated certificate provisioning and renewal 2. Integration with AWS IAM for access control 3. Monitoring and alerting for certificate status | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Enable automated alerts for expiring certificates 2. Strengthen IAM policies for certificate access 3. Conduct regular certificate audits | 1 | 4 | 108
A0147 | R0147 | Azure DDoS Protection | 3 | 3 | 3 | 27 | 1. Large-scale DDoS attacks 2. Application-layer attacks 3. Network-layer attacks | 1. Insufficient monitoring for attack patterns 2. Inadequate configuration of DDoS protection plans | 1. Service outages due to DDoS attacks 2. Reduced application performance 3. Revenue loss from downtime | 1. Automated traffic monitoring and detection 2. Integration with Azure Firewall 3. Customizable DDoS protection plans 4. Real-time attack mitigation | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Regularly review DDoS protection configurations 2. Enhance monitoring for emerging attack patterns 3. Automate incident response workflows | 1 | 4 | 108
A0148 | R0148 | Cloud Armor (GCP) | 3 | 3 | 3 | 27 | 1. Large-scale DDoS attacks 2. Application-layer attacks 3. Network-layer attacks | 1. Insufficient monitoring of traffic patterns 2. Improperly configured security policies | 1. Service disruptions due to DDoS attacks 2. Application downtime 3. Loss of revenue from service outages | 1. Predefined and custom WAF rules 2. Integration with Google Cloud Load Balancer 3. Real-time traffic analysis 4. Automatic attack mitigation | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Enhance security policy configurations 2. Regularly update WAF rules 3. Conduct ongoing traffic monitoring and assessments | 1 | 4 | 108
A0149 | R0149 | Network Security Groups (NSGs) (Azure) | 3 | 3 | 3 | 27 | 1. Unauthorized network access 2. Misconfigured security rules 3. Insider threats | 1. Weak or overly permissive rules 2. Lack of monitoring for rule changes 3. No segmentation between critical resources | 1. Data breaches due to open ports 2. Lateral movement of threats across the network 3. Compliance violations | 1. Role-based access control for NSG management 2. Real-time monitoring of rule changes 3. Traffic flow logging 4. Predefined rule templates | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Regularly review NSG rules for overly permissive configurations 2. Enhance monitoring and alerting of rule changes 3. Enforce network segmentation | 1 | 4 | 108
A0150 | R0150 | Firewall (AWS, Azure, GCP) | 3 | 3 | 3 | 27 | 1. Unauthorized access attempts 2. DDoS attacks 3. Exploitation of misconfigured rules | 1. Overly permissive firewall rules 2. Lack of real-time monitoring 3. Insufficient logging and auditing | 1. Data breaches due to unauthorized access 2. Service disruption from DDoS 3. Compliance violations | 1. Predefined security policies 2. Role-based access control (RBAC) 3. Real-time monitoring and alerts 4. Comprehensive traffic logging | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Regularly review firewall rules 2. Enhance monitoring and alerting for anomalous traffic patterns 3. Conduct periodic rule audits | 1 | 4 | 108
A0151 | R0151 | Encryption Module (HSMs) | 3 | 3 | 3 | 27 | 1. Unauthorized access to cryptographic keys 2. Key compromise 3. Insider threats 4. Physical tampering | 1. Weak physical security controls 2. Misconfigured key management policies 3. Insufficient access control for HSM APIs | 1. Data breaches from exposed keys 2. Unauthorized decryption of sensitive data 3. Loss of cryptographic integrity | 1. Physical access restrictions 2. Role-based access control (RBAC) for HSM management 3. Automated key rotation policies 4. Comprehensive logging and auditing | Effective | 2 | 5 | 135 | Priority-1 | Risk reduction | 1. Strengthen physical security for HSMs 2. Implement stricter access controls 3. Automate key lifecycle management with rotation policies | 1 | 4 | 108